## TCR Score Sheet
Colorado Department of Transportation (CDOT) Traffic Control Review (TCR)
Project: |  | Date:
Subaccount: |  | Time:
Location:
Project Engineer: |  | Prime Contractor:
Resident Engineer: |  | Traffic Control Contractor:
Reviewer: |  | Traffic Control Supervisor:
Use Yes, No, NA (Not applicable), or NC (Not Checked)
[NOTE: References are to CDOT's 2005 Standard Specifications, standard special provisions (SSP), Construction Bulletins (CB), M&S standards (M- or S-xxx-x), Construction Manual (CM), Manual on Uniform Traffic Control Devices (MUTCD), or 2002 Roadside Design Guide (RDG)]
I. | TRAFFIC CONTROL MANAGEMENT (Weight = 1) |  | Yes/No/NA | Score | Total Possible
A. | TCS's Traffic control daily diaries on file (630.10(5)) |  |  |  | 1
B. | Diaries reviewed by CDOT (CM 630.3.2) |  |  |  | 1
C. | Discrepancies...noted in diary & corrected (630.10(5)(viii)) |  |  |  | 1
D. | Night inspections conducted weekly, documented (630.10(6)) |  |  |  | 1
E. | MUTCD (Current) in CDOT field office (CM 630.3.1 #1) |  |  |  | 1
F. | Resident Engineer Traffic Control Review done (CM 630.3.1 #7, CM 630.2.2 #1) |  |  |  | 1
G. | Public Info. Spec implemented as required, including up-to-date phone message, daily phone call log, fliers, etc. (Project Special Provision 626) |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 7
II. | METHOD OF HANDLING TRAFFIC (MHT) (Weight =2) |  | Yes/No/NA | Score | Total Possible
A. | MHT on file in project records, for each work zone operation (630.09) |  |  |  | 1
B. | All CDOT Personnel and superintendents have received WZTC training (SSP 630) |  |  |  | 1
C. | MHT in compliance with TCP (630.09) |  |  |  | 1
D. | CMO prepared for major change of TCP (630.09) |  |  |  | 1
E. | MHT reviewed and initialed by Prime contractor (CM 630.2.4 #1) |  |  |  | 1
F. | MHT approved and initialed by proper CDOT person (630.09) |  |  |  | 1
G. | MHT sufficiently detailed per 630.09.
| 1. Detailed diagram (630.09(1)) |  |  |  | 1
| 2. Tabulation of devices for each phase (630.09(2)) |  |  |  | 1
| 3. MUTCD, Plans, Specs & other sources referenced (630.09(3)) |  |  |  | 1
| 4. Estab. access mtce. plan, turn around locs., equip. storage, etc. (630.09(4)) |  |  |  | 1
| 5. Pedestrian (ADA), bicycle & non vehicular access addressed (630.09(5)) |  |  |  | 1
| 6. Plan for emergency vehicle access (630.09(6)) |  |  |  | 1
H. | Vert. and horiz. clearances (630.09(7)&(8), CM 630.2.4, #7a & 7b, CB 2006-1) |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 26
III. | WORKSITE TRAFFIC CONTROL SUPERVISOR ( TCS) (Weight =1) |  | Yes/No/NA | Score | Total Possible
A. | Current ATSSA or CCA Certification on file in project records (630.10) |  |  |  | 1
B. | TCS has current flagger card (630.10) |  |  |  | 1
C. | TCS available on project (630.10, last paragraph) |  |  |  | 1
D. | TCS has current MUTCD (630.10(8)) |  |  |  | 1
E. | TCS has current TCP, MHT, M&S-Standards and revisions (630.10(8)) |  |  |  | 1
F. | TCS appropriately dressed (fluorescent orange-red or yellow-green hardhat, vest, reflectorization at night) (630.13) |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 6
IV. | FLAGGERS (Weight = 1) (see MUTCD Chapter 6E) |  | Yes/No/NA | Score | Total Possible
A. | Current flagger card (630.13(a)) |  |  |  | 1
B. | Appropriately dressed (fluorescent orange-red or yellow-green hardhat, vest, reflectorization at night). (630.13) |  |  |  | 1
C. | Proper flagging methods used (630.13, MUTCD 6E.04) |  |  |  | 1
D. | Flagger location (630.13, MUTCD 6E.05):
| 1. Visible to traffic. |  |  |  | 1
| 2. Proper distance in advance of work. |  |  |  | 1
| 3. Station illuminated at night (630.13) |  |  |  | 1
E. | "STOP/SLOW" Paddle (630.13, MUTCD 6E.03):
| 1. Correct size and shape. |  |  |  | 1
| 2. Satisfactory condition. |  |  |  | 1
| 3. Correct sheeting (Type III or fluorescent). |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 9
V. | CONSTRUCTION/MAINTENANCE SIGNING (Weight = 3) |  | Yes/No/NA | Score | Total Possible
A. | Placement (spacing/mounting height/angle/offset/sight distance) conforms to approved MHT/MUTCD/S-Stds. |  |  |  | 1
B. | Conforms to MUTCD/S-Standards/TC plans (size, layout, color). |  |  |  | 1
C. | Satisfactory condition (clean, readable, no wear/tear/wrinkling/bowing). |  |  |  | 1
D. | Temporary signs
| 1. 1' minimum above pavement elevation (S-630-1, Sht 11, note 12) |  |  |  | 1
| 2. Stored out of clear zone (630.12, SSP 630) |  |  |  | 1
E. | Satisfactory breakaway posts or NCHRP 350 compliant (630.02, 614.02, 630.08, SSP 630, CB 2005-10) |  |  |  | 1
F. | Correct signing for situation |  |  |  | 1
G. | Conflicting signs properly treated (masked, turned, removed) (630.11, 630.12) |  |  |  | 1
H. | Appropriate fluorescent & reflective sheeting on all signs. (630.02, SSP 614/630) |  |  |  | 1
I. | Flashing beacons installed/working properly (S-614-14) |  |  |  | 1
J. | VMS message/placement (MUTCD 6F.55, MUTCD 1A.14) |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 33
VI. | TRAFFIC CONTROL DEVICES (Weight =3) |  | Yes/No/NA | Score | Total Possible
A. | Arrow panel (MUTCD 6F.56, 630.03)
| 1. Correct size, number of lights etc. |  |  |  | 1
| 2. Correct mounting height. |  |  |  | 1
| 3. Correct placement. |  |  |  | 1
| 4. All lights working. |  |  |  | 1
| 5. Correct operating mode. |  |  |  | 1
| 6. Auto dimmer for night use operational. |  |  |  | 1
B. | Channelizing devices (barricades, cones, drums, etc.) (630.05, 630.06, MUTCD 6F.58 to 6F.63):
| 1. Correct dimensions. |  |  |  | 1
| 2. Clean, adequately maintained, and functional (upright, etc.) |  |  |  | 1
| 3. Correct taper length |  |  |  | 1
| 4. Correct spacing between devices. |  |  |  | 1
| 5. Warning lights working. |  |  |  | 1
C. | Concrete barrier (temporary):
| 1. Correctly pinned. (630.07, M-606-14, RDG 9.2.1.1) |  |  |  | 1
| 2. Proper reflector spacing. (S-630-2 Note 9, max 50 feet) |  |  |  | 1
| 3. Proper reflector color (S-612-1) |  |  |  | 1
| 4. End treatment installed, or “Clear zone” established. (S-630-2, Note 9) |  |  |  | 1
| 5. Correct Taper (RDG 9.2.1.1.1, 4:1 to 8:1, S-630-1, Sht 11, Note 16) |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 48
VII. | PAVEMENT MARKINGS (Weight =2) |  | Yes/No/NA | Score | Total Possible
A. | Pavement marking plan on file. (627.03) |  |  |  | 1
B. | Conflicting markings properly removed. (627.03(d), 202.05, MUTCD 6F.71) |  |  |  | 1
C. | Pavement markings placed correctly (full compliance, width, length, location, waviness) (627.03) (per plans, specs, and MUTCD) |  |  |  | 1
| 1. No passing zones in full compliance. (627.03) |  |  |  | 1
D. | Satisfactory condition (not overly faded, damaged or obscured) |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 10
VIII. | MISCELLANEOUS ITEMS (Weight = 3) |  | Yes/No/NA | Score | Total Possible
A. | “Clear Zone” free of obstructions. (per plans or RDG 9.1.1)
| 1. Construction materials/equipment out of clear zone or protected |  |  |  | 1
| 2. Hazards in clear zone (other than barrier) delineated or protected |  |  |  | 1
| 3. Pavement edge drop-offs minimized, marked if present (MUTCD 6F.42) |  |  |  | 1
B. | Impact attenuators:
| 1. Installed per specifications (proper array and pad). |  |  |  | 1
| 2. Lids in place, dry sand, good condition. |  |  |  | 1
| 3. Other attenuator types installed properly and maintained |  |  |  | 1
C. | Pilot car operation correct. (630.13) |  |  |  | 1
D. | Compliance with Project Special Provisions (working hours, etc.). |  |  |  | 1
E. | Traffic Signal operations/installation (630.04, 614)
| 1. Timing adequate |  |  |  | 1
| 2. Vertical clearance adequate/Proper location of heads |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 30
IX. | TRAFFIC IMPACTS (Weight = 2) |  | Yes/No/NA | Score | Total Possible
A. | Adequate driver guidance (Drivers understand where to go) |  |  |  | 1
B. | Traffic delays being mitigated (Alt Rte, delays advertised etc.) |  |  |  | 1
C. | Accidents documented (630.10(5)(viii)) |  |  |  | 1
D. | Work Zone speed limit
| 1. Form 568 on file (CM, Appendix B) |  |  |  | 1
| 2. Speed reduction appropriate for operation (not too slow/not too fast) |  |  |  | 1
| 3. "Fines Doubled" and return to speed limit properly placed (S-630-1, Sht 10) |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 12
X. | WORK ZONE AREA AND INSPECTOR SAFETY (Weight = 2) |  | Yes/No/NA | Score | Total Possible
A. | Safe entrance/exit to work zone for equipment and workers (630.09(4)) |  |  |  | 1
B. | Work zone buffer adequate (MUTCD 6C.06) |  |  |  | 1
|  | Section Score (Sum X Wt) |  | 0 | 4
| SUMMARY |  | Score | Total Possible | Percentage
I. | TRAFFIC CONTROL MANAGEMENT |  | 0 | 7 | 0%
II. | METHOD OF HANDLING TRAFFIC (MHT) |  | 0 | 26 | 0%
III. | WORKSITE TRAFFIC CONTROL SUPERVISOR (TCS) |  | 0 | 6 | 0%
IV. | FLAGGERS |  | 0 | 9 | 0%
V. | CONSTRUCTION/MAINTENANCE SIGNING |  | 0 | 33 | 0%
VI. | TRAFFIC CONTROL DEVICES |  | 0 | 48 | 0%
VII. | PAVEMENT MARKINGS |  | 0 | 10 | 0%
VIII. | MISCELLANEOUS ITEMS |  | 0 | 30 | 0%
IX. | TRAFFIC IMPACTS |  | 0 | 12 | 0%
X. | WORK ZONE AREA AND INSPECTOR SAFETY |  | 0 | 4 | 0%
| Project Score |  | 0 | 185 | 0%
(See next page for comments)
COMMENTS:
Note on C3: All users: This sheet is protected and all uneditable cells in this form are locked. Use the <Tab> key to navigate to editable fields. All editable cells are unlocked and data entered will appear in a blue font. To unlock the sheet choose Tools/ Protection/ Unprotect Sheet and press return …there is no password. (To hide this comment from view choose View/ Comments) RRH